## Sheet1
No. | Personnel | Duration | Task name | Week 1: Mon Feb 2 | [6 empty] | Week 2: Mon Feb 9 | [6 empty] | Week 3: Mon Feb 16 | [6 empty] | Week 4: Mon Feb 23 | [6 empty] | Week 5: Mon Mar 1 | [6 empty] | Week 6: Mon Mar 8 | [6 empty] | Week 7: Mon Mar 15 | [6 empty] | Week 8: Mon Mar 22 | [6 empty] | Week 9: Mon Mar 29
|  |  |  | M | T | W | Th | F | Sa | S | M | T | W | Th | F | Sa | S | M | T | W | Th | F | Sa | S | M | T | W | Th | F | Sa | S | M | T | W | Th | F | Sa | S | M | T | W | Th | F | Sa | S | M | T | W | Th | F | Sa | S | M | T | W | Th | F | Sa | S | M | T | W | Th | F | Sa | S
RESEARCH PHASE
1 | Nathan | 7 | Research Navigation | Week 1: Mon Feb 2 M: Task 1
2 | John | 7 | Research Pick and store | Week 1: Mon Feb 2 M: Task 2
3 | Triet | 7 | Research Barcode scanner | Week 1: Mon Feb 2 M: Task 3
4 | Bao | 7 | Research Localization | Week 1: Mon Feb 2 M: Task 4
BUILD AND TEST PHASE
5 | Nathan+ | 7 | Build navigation | Week 2: Mon Feb 9 M: Task 5
6 | Nathan+ | 7 | Test and rework: Navigation | Week 3: Mon Feb 16 M: Task 6
7 | John+ | 7 | Build Pick and store | Week 2: Mon Feb 9 M: Task 7
8 | John+ | 7 | Test and rework: Pick and store | Week 3: Mon Feb 16 M: Task 8
9 | Nathan+ | 1 | Combine Navigation + Pick | Week 4: Mon Feb 23 M: 9
10 | Triet+ | 7 | Build Barcode Scan | Week 4: Mon Feb 23 T: Task 10
11 | Triet+ | 7 | Test and rework: Barcode scan | Week 5: Mon Mar 1 M: Task 11
12 | Bao+ | 7 | Build Localization | Week 6: Mon Mar 8 M: Task 12
13 | Bao+ | 7 | Test and rework: Localization | Week 7: Mon Mar 15 M: Task 13
14 | Everyone | 7 | Final integration test and rework | Week 8: Mon Mar 22 M: Task 14
POST-DEMONSTRATION WORK
15 | Triet+ | 3 | Prepare presentation | Week 9: Mon Mar 29 M: Task 15
16 | Everyone | 1 | Give presentation | Week 9: Mon Mar 29 Th: 16
17 | Bao & Triet | 7 | Re-format engineering notebook | Week 9: Mon Mar 29 M: Task 17
18 | John & Nathan | 7 | Write report | Week 9: Mon Mar 29 M: Task 18